## Projets Jerome
Classification | Project Name | Company | Start Date | End Date | Status | Estimated Hours | Total Hours Worked | Hourly rate | Currency | Estimated Revenue | Project Number | Contract | ContractID | Create Date | Account Manager | Location | Lat | Long | Adresse | Autotask | check comp | check proj
En implantation | Implantation SAP HANA Azure + We Go Trade | Distribution GVA | 2020-10-01 | 2022-12-30 | New | 456 | 605.75 | 165 | CAD | 86526 | P20201009.0001 | Distribution GVA implantation SAP | 29684478 | 2020-10-09 | Dufour, Daniel | https://www.google.fr/maps/place/Distribution+GVA+Inc./@45.5853088,-73.7116445,17z/data=!4m13!1m7!3m6!1s0x4cc9219b39d4d33b:0x961f6a106a81006b!2s1950+Boulevard+des+Laurentides,+Laval,+QC+H7M+2Y9!3b1!8m2!3d45.5853088!4d-73.7094558!3m4!1s0x41aacc371c0c6853:0x7e5ed2e830a314af!8m2!3d45.5852879!4d-73.7094431!5m1!1e1?hl=fr | 45.5853 | -73.7095 | 1950 BOUL. des Laurentides, Laval, QC, H7M 2Y5 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=561 | Distribution GVA | Implantation SAP HANA Azure + We Go Trade
En implantation | Implantation SAP SQL Produmex | SIT Mauricie | 2021-04-11 | 2022-12-30 | In Progress | 207 | 159.75 | 155 | CAD | 36897.75 | P20210411.0002 | Projet Implantation SIT | 29684754 | 2021-04-11 | Dufour, Daniel | https://www.google.fr/maps/place/Sit+Mauricie/@46.3399901,-72.5556003,18.91z/data=!4m5!3m4!1s0x0:0xfecea68a17e43c36!8m2!3d46.3399946!4d-72.5550643!5m1!1e1?hl=fr | 46.34 | -72.5551 | 1090 Rue de la Vérendrye, Trois-Rivières, QC G9A 2S8 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=640 | SIT Mauricie | Implantation SAP SQL Produmex
ServicesPLUS | Implantation Editions Chouette | Éditions Chouette | 2021-06-28 | 2022-12-30 | In Progress | 401 | 274 | 165 | CAD | 76089.75 | P20210714.0001 | Editions Chouette-Retainer | 29685238 | 2021-07-14 | Dufour, Daniel | https://www.google.fr/maps/place/LES+%C3%89DITIONS+CHOUETTE+(1987)+inc./@45.6108288,-73.8582806,17z/data=!4m12!1m6!3m5!1s0x4cc91142da3d61ff:0xb55087171593262f!2sLES+%C3%89DITIONS+CHOUETTE+(1987)+inc.!8m2!3d45.6110368!4d-73.8562293!3m4!1s0x4cc91142da3d61ff:0xb55087171593262f!8m2!3d45.6110368!4d-73.8562293!5m1!1e1?hl=fr | 45.611 | -73.8562 | 2515 Av. de la Renaissance, Boisbriand, QC J7H 1T9 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=679 | Éditions Chouette | Implantation Editions Chouette
ServicesPLUS | Implementation SAP HANA Versago | O&T Farms | 2021-07-15 | 2022-12-30 | In Progress | 781 | 759.25 | 165 | CAD | 148194.75 | P20210715.0001 | O&T Farms Implementation project | 29684798 | 2021-07-15 | Dufour, Daniel | https://www.google.fr/maps/place/O+%26+T+Farms+Ltd/@48.1142644,-97.5674125,5z/data=!4m5!3m4!1s0x0:0x8d1b22cb14efb697!8m2!3d50.4836299!4d-104.7133565!5m1!1e1?hl=fr | 50.4836 | -104.7134 | Sherwood Drive and, Pinkie Rd, Regina, SK S4R 8R7 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=680 | O&T Farms | Implementation SAP HANA Versago
ServicesPLUS | Implantation WMS | Entreprise Tenzo inc. | 2021-08-01 | 2022-12-31 | In Progress | 202 | 76.75 | 150 | CAD | 34845 | P20210804.0002 | Projet WMS | 29684804 | 2021-08-04 | Mcenaney, Tracy | https://www.google.fr/maps/place/T%C3%ABnzo+Fine+Plomberie/@45.5975069,-73.2210645,17z/data=!3m1!4b1!4m5!3m4!1s0x4cc8555dfcbc8aeb:0xa5269fb26ea18829!8m2!3d45.5975032!4d-73.2165798!5m1!1e1?hl=fr | 45.5975 | -73.2166 | 1101 Rue Louis-Marchand, Beloeil, QC J3G 6S4 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=686 | Entreprise Tenzo inc. | Implantation WMS
ServicesPLUS | Implantation WMS | Tzanet | 2021-09-01 | 2022-12-30 | New | 200 | 103.25 | 155 | CAD | 35650 | P20210922.0001 | Retainer Tzanet- Projet Produmex WMS | 29684829 | 2021-09-22 | Mcenaney, Tracy | https://www.google.fr/maps/place/Les+Entreprises+Tzanet/@45.563041,-73.7008035,13z/data=!4m9!1m2!2m1!1stzanet!3m5!1s0x4cc918f3f22a80a9:0xc62c2032f37672a4!8m2!3d45.5332363!4d-73.6628473!15sCgZ0emFuZXQiA4gBAVoIIgZ0emFuZXSSARRraXRjaGVuX3N1cHBseV9zdG9yZeABAA!5m1!1e1?hl=fr | 45.5332 | -73.6628 | 1375 Rue de Louvain O, Montréal, QC H4N 1G6 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=702 | Tzanet | Implantation WMS
ServicesPLUS | CMBB SAP Implementation | CMBB Bakeware Canada Inc. | 2021-11-19 | 2022-12-30 | In Progress | 212 | 214.75 | 195 | CAD | 47541 | P20211119.0001 | Project SAP Implementation | 29684853 | 2021-11-19 | Dufour, Daniel | https://www.google.fr/maps/place/84+Easton+Rd,+Brantford,+ON+N3P+1J5/@43.1783099,-80.2439915,17z/data=!4m13!1m7!3m6!1s0x882c65a8c719a50d:0x6f23799d6a1e608!2s84+Easton+Rd,+Brantford,+ON+N3P+1J5!3b1!8m2!3d43.178306!4d-80.2418028!3m4!1s0x882c65a8c719a50d:0x6f23799d6a1e608!8m2!3d43.178306!4d-80.2418028!5m1!1e1?hl=fr | 43.1783 | -80.2418 | 84 Easton Road,Brantford Ontario N3P 1J5 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=716 | CMBB Bakeware Canada Inc. | CMBB SAP Implementation
ServicesPLUS | Migration SAP V10 | Cowper Inc. | 2021-12-01 | 2022-12-31 | Complete | 40 | 46.5 | 160 | CAD | 7360 | P20211202.0001 | Migration SAP V10 | 29684859 | 2021-12-02 | Champoux, Daniel | https://www.google.fr/maps/place/Cowper+Inc./@45.5056385,-73.8453642,11.77z/data=!4m5!3m4!1s0x0:0x4c8bb1af0ea42de6!8m2!3d45.4413746!4d-73.670454!5m1!1e1?hl=fr | 45.4414 | -73.6705 | 677 7th avenue, Lachine, QC | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=722 | Cowper Inc. | Migration SAP V10
ServicesPLUS | Implantation Produmex Scan | Cowper Inc. | 2022-11-28 | 2023-06-15 | New | 30 |  | 160 | CAD | 5520 | P20221128.0003 | Produmex Scan | 29685279 | 2022-11-28 | Champoux, Daniel | https://www.google.fr/maps/place/Cowper+Inc./@45.5056385,-73.8453642,11.77z/data=!4m5!3m4!1s0x0:0x4c8bb1af0ea42de6!8m2!3d45.4413746!4d-73.670454!5m1!1e1?hl=fr | 45.4414 | -73.6705 | 677 7th avenue, Lachine, QC | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=722 | Cowper Inc. | Implantation Produmex Scan
ServicesPLUS | SAP HANA Implementation | Coco Bakery Inc. | 2021-12-06 | 2022-12-30 | In Progress | 579 | 468.25 | 165 | CAD | 109865.25 | P20211206.0001 | SAP implementation project | 29684857 | 2021-12-06 | Dufour, Daniel | https://www.google.fr/maps/place/6226+Danville+Rd,+Mississauga,+ON+L5T+2H7/@43.6421185,-79.6747931,18z/data=!4m13!1m7!3m6!1s0x882b3f69ec62ad99:0xe801a6135638fab9!2s6226+Danville+Rd,+Mississauga,+ON+L5T+2H7!3b1!8m2!3d43.6421169!4d-79.6738909!3m4!1s0x882b3f69ec62ad99:0xe801a6135638fab9!8m2!3d43.6421169!4d-79.6738909!5m1!1e1?hl=fr | 43.6421 | -79.6739 | 6226 Danville Road, Mississauga, ON L5T 2H7 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=725 | Coco Bakery Inc. | SAP HANA Implementation
ServicesPLUS | Migration V10 SQL | Les Aliments CDS inc. | 2022-01-03 | 2023-01-27 | In Progress | 38 | 18.25 | 160 | CAD | 6992 | P20220104.0002 | Projet Migration V10 SQL | 29685098 | 2022-01-04 | Mcenaney, Tracy | https://www.google.fr/maps/place/Les+Aliments+CDS+Foods+Inc./@45.5275469,-73.6519625,14.4z/data=!4m5!3m4!1s0x0:0x9e5bd2d32605e06d!8m2!3d45.5284002!4d-73.6657747!5m1!1e1?hl=fr | 45.5284 | -73.6658 | 775 Bd Lebeau, Saint-Laurent, QC H4N 1S5 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=740 | Les Aliments CDS inc. | Migration V10 SQL
ServicesPLUS & ServicesTECH | Implantation SAP phase 1 et 2 | Gazebo Penguin Inc. | 2022-01-01 | 2023-02-05 | In Progress | 200 | 5 | 170 | CAD | 39100 | P20220110.0002 | Projet implantation SAP | 29685103 | 2022-01-10 | Dufour, Daniel | https://www.google.fr/maps/place/Gazebo+Penguin+Inc/@45.4710799,-73.6971059,17z/data=!3m1!4b1!4m5!3m4!1s0x4cc917bb885b926d:0x4e4996129610b8c4!8m2!3d45.4710762!4d-73.6949172!5m1!1e1?hl=fr | 45.4711 | -73.6949 | 4660 Rue Hickmore, Saint-Laurent, QC H4T 1K2 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=744 | Gazebo Penguin Inc. | Implantation SAP phase 1 et 2
ServicesPLUS | Fixed assets implementation | Walt's Wholesale Meats | 2022-02-15 | 2022-04-30 | New | 21 | 5.25 | 185 | USD | 4467.75 | P20220215.0001 | 2022 - Walt's Wholesale Meats (PLUS) | 29685081 | 2022-02-15 | Frandsen, Scott | https://www.google.fr/maps/place/350+S+Pekin+Rd,+Woodland,+WA+98674,+%C3%89tats-Unis/@45.8913918,-122.7452506,17z/data=!3m1!4b1!4m5!3m4!1s0x54944f1f45f97411:0xfa635b6193402016!8m2!3d45.8913918!4d-122.7430619!5m1!1e1?hl=fr | 45.8914 | -122.7431 | 350 S Pekin Rd , Woodland WA 98674 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=762 | Walt's Wholesale Meats | Fixed assets implementation
En implantation | Implementation SAP HANA | Lovato Electric Inc. (USA) | 2022-05-09 | 2023-02-28 | In Progress | 230 | 87.75 | 150 | USD | 39675 | P20220515.0001 | Implementation PROJECT | 29685185 | 2022-05-15 | Dufour, Daniel | https://www.google.fr/maps/place/LOVATO+Electric/@36.7919655,-76.2459392,16.59z/data=!4m5!3m4!1s0x0:0x2d8afaab31ba084e!8m2!3d36.7918965!4d-76.2460442!5m1!1e1?hl=fr | 36.7919 | -76.246 | 2017 Georgetown Blvd, Chesapeake, VA 23325, États-Unis | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=791 | Lovato Electric Inc. (USA) | Implementation SAP HANA
ServicesPLUS | Implantation SAP | Megastar Électroniques Inc. | 2022-09-16 | 2023-04-28 | In Progress | 407 | 9 | 185 | CAD | 86589.25 | P20220916.0001 | Projet MegaStar | 29685237 | 2022-09-16 | Dufour, Daniel | https://www.google.fr/maps/place/Mega+Star+Electronics/@45.5959339,-73.6251983,17z/data=!4m13!1m7!3m6!1s0x4cc91f0eb603ccf1:0x98b53f098eaf6dc4!2s5061+Rue+d'Amiens,+Montr%C3%A9al-Nord,+QC+H1G+3G2!3b1!8m2!3d45.5959339!4d-73.6230096!3m4!1s0x4cc91f0eb6183d4d:0x160e294c414f78c1!8m2!3d45.5960346!4d-73.6228044!5m1!1e1?hl=fr | 45.5959 | -73.623 | 5061 Rue d'Amiens, Montréal-Nord, QC H1G 3G2 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=829 | Megastar Électroniques Inc. | Implantation SAP
ServicesPLUS | Migration SAP V10 SQL | Laiterie de Coaticook ltée | 2022-09-16 | 2022-12-30 | Complete | 56 | 31.75 | 165 | CAD | 10626 | P20220922.0001 | Migration SAP V10 SQL | 29685240 | 2022-09-22 | Champoux, Daniel | https://www.google.fr/maps/place/Laiterie+de+Coaticook+Lt%C3%A9e/@45.1569719,-71.8032584,17z/data=!3m1!4b1!4m5!3m4!1s0x4cb658f0bcef7741:0xb18492fd3db72d09!8m2!3d45.1569295!4d-71.8010503!5m1!1e1?hl=fr | 45.1569 | -71.8011 | 1000 Rue Child, Coaticook, QC J1A 2S5 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=830&restoreworkspacekey= | Laiterie de Coaticook ltée | Migration SAP V10 SQL
ServicesPLUS & ServicesTECH | SAP V10 Migration | Federal Steel Equipment Ltd. | 2022-10-05 | 2023-03-30 | New | 16 | 11 | 165 | CAD | 3036 | P20221005.0002 | Projet migration | 29685243 | 2022-10-05 | Champoux, Daniel | https://www.google.com/maps/place/Federal+Steel+Equipment+Ltd/@45.438671,-73.6842559,17z/data=!4m12!1m6!3m5!1s0x4cc916ed91b1a055:0x25f4359a9b7f9fcd!2sFederal+Steel+Equipment+Ltd!8m2!3d45.4386681!4d-73.6822375!3m4!1s0x4cc916ed91b1a055:0x25f4359a9b7f9fcd!8m2!3d45.4386681!4d-73.6822375 | 45.4387 | -73.6822 | 540 20e Avenue, Lachine, QC H8S 3T1 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=835 | Federal Steel Equipment Ltd. | SAP V10 Migration
ServicesPLUS & ServicesTECH | Installation serveur | Federal Steel Equipment Ltd. | 2022-10-05 | 2023-03-30 | New | 40 | 0 | 135 | CAD | 6210 | P20221124.0001 | Installation d'un nouveau serveur | 29685276 | 2022-11-28 | Champoux, Daniel | https://www.google.com/maps/place/Federal+Steel+Equipment+Ltd/@45.438671,-73.6842559,17z/data=!4m12!1m6!3m5!1s0x4cc916ed91b1a055:0x25f4359a9b7f9fcd!2sFederal+Steel+Equipment+Ltd!8m2!3d45.4386681!4d-73.6822375!3m4!1s0x4cc916ed91b1a055:0x25f4359a9b7f9fcd!8m2!3d45.4386681!4d-73.6822375 | 45.4387 | -73.6822 | 540 20e Avenue, Lachine, QC H8S 3T1 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=856 | #N/A | #N/A
ServicesPLUS & ServicesTECH | Support pour questions | Federal Steel Equipment Ltd. | 2022-10-05 | 2023-03-30 | New | 30 | 21.75 | 165 | CAD | 5692.5 | P20220802.0001 | Formation générale 2022 - Support AdHoc | 29685224 | 2022-08-02 | Champoux, Daniel | https://www.google.com/maps/place/Federal+Steel+Equipment+Ltd/@45.438671,-73.6842559,17z/data=!4m12!1m6!3m5!1s0x4cc916ed91b1a055:0x25f4359a9b7f9fcd!2sFederal+Steel+Equipment+Ltd!8m2!3d45.4386681!4d-73.6822375!3m4!1s0x4cc916ed91b1a055:0x25f4359a9b7f9fcd!8m2!3d45.4386681!4d-73.6822375 | 45.4387 | -73.6822 | 540 20e Avenue, Lachine, QC H8S 3T1 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=810 | #N/A | #N/A
ServicesPLUS | SAP V10 Migration | Groupe Pro-Fab | 2022-11-30 | 2023-03-30 | New | 78 |  | 175 | CAD | 15697.5 | P20221212.0001 | Migration SAP B1 V9.1 vers V10 | 29685280 | 2022-12-06 | Champoux, Daniel | https://www.google.fr/maps/place/Groupe+Pro-Fab+-+Si%C3%A8ge+social/@46.6231521,-71.5027654,17z/data=!4m5!3m4!1s0x0:0x46eb83a9a3cadc17!8m2!3d46.6235537!4d-71.5004496!5m1!1e1?hl=fr | 46.6236 | -71.5004 | 294 Rue Laurier, Saint-Apollinaire, QC G0S 2E0 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=864 | #N/A | #N/A
ServicesPLUS | Migration SAP B1 V10 SQL | Produit Electrolation | 2022-12-22 | 2023-03-30 | New | 46 |  | 165 | CAD | 8728.5 | P20221222.0001 | Migration V10 SQL | 29685283 | 2022-12-22 | Carriere, Daniel | https://www.google.fr/maps/place/Produits+Electrolation+Inc/@45.594032,-73.7443942,19z/data=!4m12!1m6!3m5!1s0x4cc92143ec29647d:0x9f89ab8988471bbd!2sProduits+Electrolation+Inc!8m2!3d45.5943373!4d-73.7441876!3m4!1s0x4cc92143ec29647d:0x9f89ab8988471bbd!8m2!3d45.5943373!4d-73.7441876!5m1!1e1?hl=fr | 45.5943 | -73.7442 | 990 Rue Bergar Laval QC H7L 5A1 CANADA | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=866
ServicesPLUS | Produmex WMS | Laiterie de Coaticook ltée | 2022-10-24 | 2023-03-31 | New | 166 | 1 | 165 | CAD | 31498.5 | P20221024.0001 | Produmex WMS | 29685255 | 2022-10-24 | Champoux, Daniel | https://www.google.fr/maps/place/Laiterie+de+Coaticook+Lt%C3%A9e/@45.1569719,-71.8032584,17z/data=!3m1!4b1!4m5!3m4!1s0x4cb658f0bcef7741:0xb18492fd3db72d09!8m2!3d45.1569295!4d-71.8010503!5m1!1e1?hl=fr | 45.1569 | -71.8011 | 1000 Rue Child, Coaticook, QC J1A 2S5 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=830&restoreworkspacekey= | Laiterie de Coaticook ltée | Produmex WMS
En implantation | Implantation SAP B1 & Process Force | Fromagerie Polyethnique Inc | 2022-11-01 | 2023-12-31 | New | 815 | 1 | 170 | CAD | 159332.5 | P20221111.0001 | Projet implantation SAP B1 | 29685265 | 2022-11-11 | Dufour, Daniel | https://www.google.fr/maps/place/Fromagerie+Polyethnique+Inc./@45.9439944,-73.0552781,12.05z/data=!4m5!3m4!1s0x0:0xef280bcfed15fb50!8m2!3d45.9290294!4d-73.0172073!5m1!1e1?hl=fr | 45.929 | -73.0172 | 235 Chemin de St Robert, Saint-Robert, QC J0G 1S0 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=852 | Fromagerie Polyethnique Inc | Implantation SAP B1 & Process Force
En implantation | Projet implantation SAP et WMS | Groupe Carreaux Céragrès Inc. | 2022-10-12 | 2023-12-29 | In Progress | 981 | 93.5 | 165 | CAD | 186144.75 | P20221012.0001 | Projet implantation SAP et WMS | 29685241 | 2022-10-12 | Dufour, Daniel | https://www.google.fr/maps/place/825+Rue+Deslauriers,+Saint-Laurent,+QC+H4N+1X3/@45.5292868,-73.667034,17z/data=!4m12!1m6!3m5!1s0x4cc9185f4cc42355:0xad548e4af066f4c6!2sGroupe+Carreaux+C%C3%A9ragr%C3%A8s+Inc.+(si%C3%A8ge+social)+-+Ceragres+Tile+Group+Inc.+(head+office)!8m2!3d45.5292868!4d-73.6648453!3m4!1s0x4cc9185f5a99d0af:0xb101086266c8cfcb!8m2!3d45.5292868!4d-73.6648453!5m1!1e1?hl=fr | 45.5293 | -73.6648 | 825 Deslaurier, Montreal QC H4N 1X3 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=837 | Groupe Carreaux Céragrès Inc. | Projet implantation SAP et WMS
ServicesPLUS | Dubois Agrinovations - Archivage | Dubois Agrinovation Inc. | 2022-11-16 | 2023-05-06 | New | 33 | 3.5 | 170 | CAD | 6451.5 | P20221121.0001 | 2022 - Standard - Dubois Agrinovation (PLUS) | 29685117 | 2022-11-21 | Dufour, Daniel | https://www.google.fr/maps/place/Dubois+Agrinovation+-+%C3%89quipement+%26+Outils+d'Irrigation+et+Agricole/@45.2710103,-73.6095246,17z/data=!4m13!1m7!3m6!1s0x4cc97240123b9b5d:0x405a2402c5924169!2s478+Rue+Notre+Dame,+Saint-R%C3%A9mi,+QC+J0L+2L0!3b1!8m2!3d45.2710103!4d-73.6073359!3m4!1s0x4cc97240004f7b63:0xa00d36f88582c8ce!8m2!3d45.2708914!4d-73.607322!5m1!1e1?hl=fr | 45.271 | -73.6073 | 478 Rue Notre Dame, Saint-Rémi, QC J0L 2L0 | https://ww14.autotask.net/Mvc/Framework/Navigation.mvc/Landing?restoreworkspacekey=z3f7cb84a3a934ef3ad2d0dc3eee18d6c | Dubois Agrinovation Inc. | Dubois Agrinovations - Archivage
|  | Forgestik - Quebec | [7 empty] | 0 | [5 empty] | https://www.google.fr/maps/place/Forgestik+Inc.+-+Qu%C3%A9bec/@46.7678083,-71.2910004,17z/data=!4m5!3m4!1s0x0:0x3410c520d6b20abc!8m2!3d46.7677269!4d-71.2887151!5m1!1e1?hl=fr | 46.7677 | -71.2887 | 2828 Bd Laurier #700, Québec, QC G1V 0B9 |  | 0 | 0
|  | Forgestik-Montreal | [7 empty] | 0 | [5 empty] | https://www.google.fr/maps/place/Forgestik+Inc+-+Montreal+Head+Office/@45.5219334,-73.6152552,17z/data=!3m1!4b1!4m5!3m4!1s0x4cc9199df6b7f653:0x801060272b57c4f4!8m2!3d45.52193!4d-73.6130697!5m1!1e1?hl=fr | 45.5219 | -73.6131 | 797 Champagneur Avenue, Outremont, Quebec, H2V 3P9 |  | 0 | 0
|  | Forgestik - Vancouver | [7 empty] | 0 | [5 empty] | https://www.google.fr/maps/place/Forgestik+Inc+-+Vancouver/@49.2838546,-123.121829,17z/data=!3m1!5s0x548671a3d041e691:0x16e05f12b932f59a!4m12!1m6!3m5!1s0x54867181e140b2c3:0x3257d5499dc7de7c!2sForgestik+Inc+-+Vancouver!8m2!3d49.2838546!4d-123.1196403!3m4!1s0x54867181e140b2c3:0x3257d5499dc7de7c!8m2!3d49.2838546!4d-123.1196403!5m1!1e1?hl=fr | 49.2839 | -123.1196 | 885 W Georgia St #1500, Vancouver, BC V6C 3E8 |  | 0 | 0
|  | Forgestik - Toronto | [7 empty] | 0 | [5 empty] | https://www.google.fr/maps/place/Forgestik+Inc.+-+Toronto/@43.6410825,-79.3809083,17z/data=!3m1!5s0x882b3757de085e91:0xc359f58994eb5f5!4m12!1m6!3m5!1s0x89d4cb2ae8a1ac2d:0xe007d130adfb1a56!2sForgestik+Inc.+-+Toronto!8m2!3d43.6410825!4d-79.3787196!3m4!1s0x89d4cb2ae8a1ac2d:0xe007d130adfb1a56!8m2!3d43.6410825!4d-79.3787196!5m1!1e1?hl=fr | 43.6411 | -79.3787 | 88 Queens Quay W #2500, Toronto, ON M5J 0B9 |  | 0 | 0
[10 empty] | 0 |  |  | #N/A
[10 empty] | 0 |  |  | #N/A
[10 empty] | 0 |  |  | #N/A
[10 empty] | 0 |  |  | #N/A
[10 empty] | 0 |  |  | #N/A
[10 empty] | 0 |  |  | #N/A
[10 empty] | 0 |  |  | #N/A
[10 empty] | 0 |  |  | #N/A
[10 empty] | 0 |  |  | #N/A | [8 empty] | Ceragres | 45.5275 | -73.652 | https://www.google.fr/maps/place/Groupe+Carreaux+C%C3%A9ragr%C3%A8s+Inc.+(si%C3%A8ge+social)+-+Ceragres+Tile+Group+Inc.+(head+office)/@45.5275469,-73.6519625,14.4z/data=!4m5!3m4!1s0x0:0xad548e4af066f4c6!8m2!3d45.5292868!4d-73.6648453!5m1!1e1?hl=fr
[5 empty] | TOTAL | 6265 | 2997 |  |  | 1198731.25

## import
Classification | Project Name | Company | Start Date | End Date | Status | Estimated Hours | Total Hours Worked | Estimated Revenue | Project Number | Contract | Create Date | Account Manager | Contract ID | check num proj
ServicesPLUS | CMBB SAP Implementation | CMBB Bakeware Canada Inc. | 19/11/2021 | 30/12/2022 | In Progress | 212 | 220.25 | 0 | P20211119.0001 | Project SAP Implementation | 19/11/2021 12:00 AM | Dufour, Daniel | 29684853 | CMBB Bakeware Canada Inc.
ServicesPLUS | SAP HANA Implementation | Coco Bakery Inc. | 2021-06-12 | 30/12/2022 | In Progress | 579 | 474.25 | 0 | P20211206.0001 | SAP implementation project | 2021-06-12 | Dufour, Daniel | 29684857 | Coco Bakery Inc.
ServicesPLUS | Migration SAP V10 | Cowper Inc. | 2021-01-12 | 31/12/2022 | New | 40 | 83.75 | 0 | P20211202.0001 | Migration SAP V10 | 2021-02-12 | Champoux, Daniel | 29684859 | Cowper Inc.
ServicesPLUS | Implantation Produmex Scan | Cowper Inc. | 28/11/2022 | 15/06/2023 | New | 25 | 1 | 5400 | P20221128.0003 | Produmex Scan | 28/11/2022 12:00 AM | Champoux, Daniel | 29685279 | Cowper Inc.
En implantation / Implementation | Implantation SAP HANA Azure + We Go Trade | Distribution GVA | 2020-01-10 | 30/12/2022 | New | 456 | 612.75 | 0 | P20201009.0001 | Distribution GVA implantation SAP | 2020-09-10 | Dufour, Daniel | 29684478 | Distribution GVA
ServicesPLUS | Dubois Agrinovations - Archivage | Dubois Agrinovation Inc. | 16/11/2022 | 2023-06-05 | New | 33 | 4.25 | 6451.5 | P20221121.0001 | 2022 - Standard - Dubois Agrinovation (PLUS) | 21/11/2022 12:00 AM | Dufour, Daniel | 29685117 | Dubois Agrinovation Inc.
ServicesPLUS | Implantation Editions Chouette | Éditions Chouette | 28/06/2021 | 30/12/2022 | In Progress | 401 | 281.75 | 0 | P20210714.0001 | Editions Chouette-Retainer | 14/07/2021 12:00 AM | Dufour, Daniel | 29685238 | Éditions Chouette
ServicesPLUS | Implantation WMS | Entreprise Tenzo inc. | 2021-01-08 | 2022-05-08 | In Progress | 266 | 76.75 | 0 | P20210804.0002 | Projet WMS | 2021-04-08 | Mcenaney, Tracy | 29684804 | Entreprise Tenzo inc.
ServicesPLUS & ServicesTECH | SAP V10 Migration | Federal Steel Equipment Ltd. | 2022-05-10 | 2022-06-10 | New | 16 | 11 | 0 | P20221005.0002 | Projet migration | 2022-05-10 | Champoux, Daniel | 29685243 | Federal Steel Equipment Ltd.
En implantation / Implementation | Implantation SAP B1 & Process Force | Fromagerie Polyethnique Inc | 2022-01-11 | 31/12/2023 | New | 815 | 2.25 | 0 | P20221111.0001 | Projet implantation SAP B1 | 2022-11-11 | Dufour, Daniel | 29685265 | Fromagerie Polyethnique Inc
ServicesPLUS & ServicesTECH | Implantation SAP phase 1 et 2 | Gazebo Penguin Inc. | 2022-01-01 | 2023-05-02 | In Progress | 24 | 6.5 | 0 | P20220110.0002 | Projet implantation SAP | 2022-10-01 | Dufour, Daniel | 29685103 | Gazebo Penguin Inc.
En implantation / Implementation | Projet implantation SAP et WMS | Groupe Carreaux Céragrès Inc. | 2022-12-10 | 29/12/2023 | In Progress | 983 | 142.75 | 0 | P20221012.0001 | Projet implantation SAP et WMS | 2022-12-10 | Dufour, Daniel | 29685241 | Groupe Carreaux Céragrès Inc.
ServicesPLUS | Produmex WMS | Laiterie de Coaticook ltée | 24/10/2022 | 31/03/2023 | New | 166 | 24.75 | 0 | P20221024.0001 | Produmex WMS | 24/10/2022 12:00 AM | Champoux, Daniel | 29685255 | Laiterie de Coaticook ltée
ServicesPLUS | Migration SAP V10 SQL | Laiterie de Coaticook ltée | 16/09/2022 | 30/12/2022 | New | 56 | 68.75 | 0 | P20220922.0001 | Migration SAP V10 SQL | 22/09/2022 12:00 AM | Champoux, Daniel | 29685240 | Laiterie de Coaticook ltée
ServicesPLUS | Migration V10 SQL | Les Aliments CDS inc. | 2022-03-01 | 27/01/2023 | In Progress | 38 | 20.75 | 0 | P20220104.0002 | Projet Migration V10 SQL | 2022-04-01 | Mcenaney, Tracy | 29685098 | Les Aliments CDS inc.
En implantation / Implementation | Implementation SAP HANA | Lovato Electric Inc. (USA) | 2022-09-05 | 28/02/2023 | In Progress | 230 | 123 | 0 | P20220515.0001 | Implementation PROJECT | 15/05/2022 12:00 AM | Dufour, Daniel | 29685185 | Lovato Electric Inc. (USA)
ServicesPLUS | Implantation SAP | Megastar Électroniques Inc. | 16/09/2022 | 28/04/2023 | In Progress | 407 | 32.75 | 0 | P20220916.0001 | Projet MegaStar | 16/09/2022 12:00 AM | Dufour, Daniel | 29685237 | Megastar Électroniques Inc.
ServicesPLUS | Implementation SAP HANA Versago | O&T Farms | 15/07/2021 | 30/12/2022 | In Progress | 781 | 791.5 | 0 | P20210715.0001 | O&T Farms Implementation project | 15/07/2021 12:00 AM | Dufour, Daniel | 29684798 | O&T Farms
En implantation / Implementation | Implantation SAP SQL Produmex | SIT Mauricie | 2021-11-04 | 30/12/2022 | In Progress | 207 | 171 | 0 | P20210411.0002 | Projet Implantation SIT | 2021-11-04 | Dufour, Daniel | 29684754 | SIT Mauricie
ServicesPLUS | Implantation WMS | Tzanet | 2021-01-09 | 30/12/2022 | New | 200 | 110.5 | 0 | P20210922.0001 | Retainer Tzanet- Projet Produmex WMS | 22/09/2021 12:00 AM | Mcenaney, Tracy | 29684829 | Tzanet
ServicesPLUS | Fixed assets implementation | Walt's Wholesale Meats | 15/02/2022 | 30/04/2022 | New | 21 | 5.25 | 0 | P20220215.0001 | 2022 - Walt's Wholesale Meats (PLUS) | 15/02/2022 12:00 AM | Frandsen, Scott | 29685081 | Walt's Wholesale Meats

## Projets Jerome_2
Classification | Project Name | Company | Start Date | End Date | Status | Estimated Hours | Total Hours Worked | Hourly rate | Currency | Estimated Revenue | Project Number | Contract | ContractID | Create Date | Account Manager | Location | Lat | Long | Adresse | Autotask
En implantation | Implantation SAP HANA Azure + We Go Trade | Distribution GVA | 2020-10-01 | 2022-12-30 | New | 456 | 605.75 | 165 | CAD | 86526 | P20201009.0001 | Distribution GVA implantation SAP | 29684478 | 2020-10-09 | Dufour, Daniel | https://www.google.fr/maps/place/Distribution+GVA+Inc./@45.5853088,-73.7116445,17z/data=!4m13!1m7!3m6!1s0x4cc9219b39d4d33b:0x961f6a106a81006b!2s1950+Boulevard+des+Laurentides,+Laval,+QC+H7M+2Y9!3b1!8m2!3d45.5853088!4d-73.7094558!3m4!1s0x41aacc371c0c6853:0x7e5ed2e830a314af!8m2!3d45.5852879!4d-73.7094431!5m1!1e1?hl=fr | 45.5853 | -73.7095 | 1950 BOUL. des Laurentides, Laval, QC, H7M 2Y5 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=561
En implantation | Implantation SAP SQL Produmex | SIT Mauricie | 2021-04-11 | 2022-12-30 | In Progress | 207 | 159.75 | 155 | CAD | 36897.75 | P20210411.0002 | Projet Implantation SIT | 29684754 | 2021-04-11 | Dufour, Daniel | https://www.google.fr/maps/place/Sit+Mauricie/@46.3399901,-72.5556003,18.91z/data=!4m5!3m4!1s0x0:0xfecea68a17e43c36!8m2!3d46.3399946!4d-72.5550643!5m1!1e1?hl=fr | 46.34 | -72.5551 | 1090 Rue de la Vérendrye, Trois-Rivières, QC G9A 2S8 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=640
ServicesPLUS | Implantation Editions Chouette | Éditions Chouette | 2021-06-28 | 2022-12-30 | In Progress | 401 | 274 | 165 | CAD | 76089.75 | P20210714.0001 | Editions Chouette-Retainer | 29685238 | 2021-07-14 | Dufour, Daniel | https://www.google.fr/maps/place/LES+%C3%89DITIONS+CHOUETTE+(1987)+inc./@45.6108288,-73.8582806,17z/data=!4m12!1m6!3m5!1s0x4cc91142da3d61ff:0xb55087171593262f!2sLES+%C3%89DITIONS+CHOUETTE+(1987)+inc.!8m2!3d45.6110368!4d-73.8562293!3m4!1s0x4cc91142da3d61ff:0xb55087171593262f!8m2!3d45.6110368!4d-73.8562293!5m1!1e1?hl=fr | 45.611 | -73.8562 | 2515 Av. de la Renaissance, Boisbriand, QC J7H 1T9 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=679
ServicesPLUS | Implementation SAP HANA Versago | O&T Farms | 2021-07-15 | 2022-12-30 | In Progress | 781 | 759.25 | 165 | CAD | 148194.75 | P20210715.0001 | O&T Farms Implementation project | 29684798 | 2021-07-15 | Dufour, Daniel | https://www.google.fr/maps/place/O+%26+T+Farms+Ltd/@48.1142644,-97.5674125,5z/data=!4m5!3m4!1s0x0:0x8d1b22cb14efb697!8m2!3d50.4836299!4d-104.7133565!5m1!1e1?hl=fr | 50.4836 | -104.7134 | Sherwood Drive and, Pinkie Rd, Regina, SK S4R 8R7 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=680
ServicesPLUS | Implantation WMS | Entreprise Tenzo inc. | 2021-08-01 | 2022-12-31 | In Progress | 202 | 76.75 | 150 | CAD | 34845 | P20210804.0002 | Projet WMS | 29684804 | 2021-08-04 | Mcenaney, Tracy | https://www.google.fr/maps/place/T%C3%ABnzo+Fine+Plomberie/@45.5975069,-73.2210645,17z/data=!3m1!4b1!4m5!3m4!1s0x4cc8555dfcbc8aeb:0xa5269fb26ea18829!8m2!3d45.5975032!4d-73.2165798!5m1!1e1?hl=fr | 45.5975 | -73.2166 | 1101 Rue Louis-Marchand, Beloeil, QC J3G 6S4 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=686
ServicesPLUS | Implantation WMS | Tzanet | 2021-09-01 | 2022-12-30 | New | 200 | 103.25 | 155 | CAD | 35650 | P20210922.0001 | Retainer Tzanet- Projet Produmex WMS | 29684829 | 2021-09-22 | Mcenaney, Tracy | https://www.google.fr/maps/place/Les+Entreprises+Tzanet/@45.563041,-73.7008035,13z/data=!4m9!1m2!2m1!1stzanet!3m5!1s0x4cc918f3f22a80a9:0xc62c2032f37672a4!8m2!3d45.5332363!4d-73.6628473!15sCgZ0emFuZXQiA4gBAVoIIgZ0emFuZXSSARRraXRjaGVuX3N1cHBseV9zdG9yZeABAA!5m1!1e1?hl=fr | 45.5332 | -73.6628 | 1375 Rue de Louvain O, Montréal, QC H4N 1G6 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=702
ServicesPLUS | CMBB SAP Implementation | CMBB Bakeware Canada Inc. | 2021-11-19 | 2022-12-30 | In Progress | 212 | 214.75 | 195 | CAD | 47541 | P20211119.0001 | Project SAP Implementation | 29684853 | 2021-11-19 | Dufour, Daniel | https://www.google.fr/maps/place/84+Easton+Rd,+Brantford,+ON+N3P+1J5/@43.1783099,-80.2439915,17z/data=!4m13!1m7!3m6!1s0x882c65a8c719a50d:0x6f23799d6a1e608!2s84+Easton+Rd,+Brantford,+ON+N3P+1J5!3b1!8m2!3d43.178306!4d-80.2418028!3m4!1s0x882c65a8c719a50d:0x6f23799d6a1e608!8m2!3d43.178306!4d-80.2418028!5m1!1e1?hl=fr | 43.1783 | -80.2418 | 84 Easton Road,Brantford Ontario N3P 1J5 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=716
ServicesPLUS | Migration SAP V10 | Cowper Inc. | 2021-12-01 | 2022-12-31 | Complete | 40 | 46.5 | 160 | CAD | 7360 | P20211202.0001 | Migration SAP V10 | 29684859 | 2021-12-02 | Champoux, Daniel | https://www.google.fr/maps/place/Cowper+Inc./@45.5056385,-73.8453642,11.77z/data=!4m5!3m4!1s0x0:0x4c8bb1af0ea42de6!8m2!3d45.4413746!4d-73.670454!5m1!1e1?hl=fr | 45.4414 | -73.6705 | 677 7th avenue, Lachine, QC | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=722
ServicesPLUS | Implantation Produmex Scan | Cowper Inc. | 2022-11-28 | 2023-06-15 | New | 30 |  | 160 | CAD | 5520 | P20221128.0003 | Produmex Scan | 29685279 | 2022-11-28 | Champoux, Daniel | https://www.google.fr/maps/place/Cowper+Inc./@45.5056385,-73.8453642,11.77z/data=!4m5!3m4!1s0x0:0x4c8bb1af0ea42de6!8m2!3d45.4413746!4d-73.670454!5m1!1e1?hl=fr | 45.4414 | -73.6705 | 677 7th avenue, Lachine, QC | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=722
ServicesPLUS | SAP HANA Implementation | Coco Bakery Inc. | 2021-12-06 | 2022-12-30 | In Progress | 579 | 468.25 | 165 | CAD | 109865.25 | P20211206.0001 | SAP implementation project | 29684857 | 2021-12-06 | Dufour, Daniel | https://www.google.fr/maps/place/6226+Danville+Rd,+Mississauga,+ON+L5T+2H7/@43.6421185,-79.6747931,18z/data=!4m13!1m7!3m6!1s0x882b3f69ec62ad99:0xe801a6135638fab9!2s6226+Danville+Rd,+Mississauga,+ON+L5T+2H7!3b1!8m2!3d43.6421169!4d-79.6738909!3m4!1s0x882b3f69ec62ad99:0xe801a6135638fab9!8m2!3d43.6421169!4d-79.6738909!5m1!1e1?hl=fr | 43.6421 | -79.6739 | 6226 Danville Road, Mississauga, ON L5T 2H7 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=725
ServicesPLUS | Migration V10 SQL | Les Aliments CDS inc. | 2022-01-03 | 2023-01-27 | In Progress | 38 | 18.25 | 160 | CAD | 6992 | P20220104.0002 | Projet Migration V10 SQL | 29685098 | 2022-01-04 | Mcenaney, Tracy | https://www.google.fr/maps/place/Les+Aliments+CDS+Foods+Inc./@45.5275469,-73.6519625,14.4z/data=!4m5!3m4!1s0x0:0x9e5bd2d32605e06d!8m2!3d45.5284002!4d-73.6657747!5m1!1e1?hl=fr | 45.5284 | -73.6658 | 775 Bd Lebeau, Saint-Laurent, QC H4N 1S5 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=740
ServicesPLUS & ServicesTECH | Implantation SAP phase 1 et 2 | Gazebo Penguin Inc. | 2022-01-01 | 2023-02-05 | In Progress | 200 | 5 | 170 | CAD | 39100 | P20220110.0002 | Projet implantation SAP | 29685103 | 2022-01-10 | Dufour, Daniel | https://www.google.fr/maps/place/Gazebo+Penguin+Inc/@45.4710799,-73.6971059,17z/data=!3m1!4b1!4m5!3m4!1s0x4cc917bb885b926d:0x4e4996129610b8c4!8m2!3d45.4710762!4d-73.6949172!5m1!1e1?hl=fr | 45.4711 | -73.6949 | 4660 Rue Hickmore, Saint-Laurent, QC H4T 1K2 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=744
ServicesPLUS | Fixed assets implementation | Walt's Wholesale Meats | 2022-02-15 | 2022-04-30 | New | 21 | 5.25 | 185 | USD | 4467.75 | P20220215.0001 | 2022 - Walt's Wholesale Meats (PLUS) | 29685081 | 2022-02-15 | Frandsen, Scott | https://www.google.fr/maps/place/350+S+Pekin+Rd,+Woodland,+WA+98674,+%C3%89tats-Unis/@45.8913918,-122.7452506,17z/data=!3m1!4b1!4m5!3m4!1s0x54944f1f45f97411:0xfa635b6193402016!8m2!3d45.8913918!4d-122.7430619!5m1!1e1?hl=fr | 45.8914 | -122.7431 | 350 S Pekin Rd , Woodland WA 98674 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=762
En implantation | Implementation SAP HANA | Lovato Electric Inc. (USA) | 2022-05-09 | 2023-02-28 | In Progress | 230 | 87.75 | 150 | USD | 39675 | P20220515.0001 | Implementation PROJECT | 29685185 | 2022-05-15 | Dufour, Daniel | https://www.google.fr/maps/place/LOVATO+Electric/@36.7919655,-76.2459392,16.59z/data=!4m5!3m4!1s0x0:0x2d8afaab31ba084e!8m2!3d36.7918965!4d-76.2460442!5m1!1e1?hl=fr | 36.7919 | -76.246 | 2017 Georgetown Blvd, Chesapeake, VA 23325, États-Unis | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=791
ServicesPLUS | Implantation SAP | Megastar Électroniques Inc. | 2022-09-16 | 2023-04-28 | In Progress | 407 | 9 | 185 | CAD | 86589.25 | P20220916.0001 | Projet MegaStar | 29685237 | 2022-09-16 | Dufour, Daniel | https://www.google.fr/maps/place/Mega+Star+Electronics/@45.5959339,-73.6251983,17z/data=!4m13!1m7!3m6!1s0x4cc91f0eb603ccf1:0x98b53f098eaf6dc4!2s5061+Rue+d'Amiens,+Montr%C3%A9al-Nord,+QC+H1G+3G2!3b1!8m2!3d45.5959339!4d-73.6230096!3m4!1s0x4cc91f0eb6183d4d:0x160e294c414f78c1!8m2!3d45.5960346!4d-73.6228044!5m1!1e1?hl=fr | 45.5959 | -73.623 | 5061 Rue d'Amiens, Montréal-Nord, QC H1G 3G2 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=829
ServicesPLUS | Migration SAP V10 SQL | Laiterie de Coaticook ltée | 2022-09-16 | 2022-12-30 | Complete | 56 | 31.75 | 165 | CAD | 10626 | P20220922.0001 | Migration SAP V10 SQL | 29685240 | 2022-09-22 | Champoux, Daniel | https://www.google.fr/maps/place/Laiterie+de+Coaticook+Lt%C3%A9e/@45.1569719,-71.8032584,17z/data=!3m1!4b1!4m5!3m4!1s0x4cb658f0bcef7741:0xb18492fd3db72d09!8m2!3d45.1569295!4d-71.8010503!5m1!1e1?hl=fr | 45.1569 | -71.8011 | 1000 Rue Child, Coaticook, QC J1A 2S5 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=830&restoreworkspacekey=
ServicesPLUS & ServicesTECH | SAP V10 Migration | Federal Steel Equipment Ltd. | 2022-10-05 | 2023-03-30 | New | 16 | 11 | 165 | CAD | 3036 | P20221005.0002 | Projet migration | 29685243 | 2022-10-05 | Champoux, Daniel | https://www.google.com/maps/place/Federal+Steel+Equipment+Ltd/@45.438671,-73.6842559,17z/data=!4m12!1m6!3m5!1s0x4cc916ed91b1a055:0x25f4359a9b7f9fcd!2sFederal+Steel+Equipment+Ltd!8m2!3d45.4386681!4d-73.6822375!3m4!1s0x4cc916ed91b1a055:0x25f4359a9b7f9fcd!8m2!3d45.4386681!4d-73.6822375 | 45.4387 | -73.6822 | 540 20e Avenue, Lachine, QC H8S 3T1 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=835
ServicesPLUS & ServicesTECH | Installation serveur | Federal Steel Equipment Ltd. | 2022-10-05 | 2023-03-30 | New | 40 | 0 | 135 | CAD | 6210 | P20221124.0001 | Installation d'un nouveau serveur | 29685276 | 2022-11-28 | Champoux, Daniel | https://www.google.com/maps/place/Federal+Steel+Equipment+Ltd/@45.438671,-73.6842559,17z/data=!4m12!1m6!3m5!1s0x4cc916ed91b1a055:0x25f4359a9b7f9fcd!2sFederal+Steel+Equipment+Ltd!8m2!3d45.4386681!4d-73.6822375!3m4!1s0x4cc916ed91b1a055:0x25f4359a9b7f9fcd!8m2!3d45.4386681!4d-73.6822375 | 45.4387 | -73.6822 | 540 20e Avenue, Lachine, QC H8S 3T1 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=856
ServicesPLUS & ServicesTECH | Support pour questions | Federal Steel Equipment Ltd. | 2022-10-05 | 2023-03-30 | New | 30 | 21.75 | 165 | CAD | 5692.5 | P20220802.0001 | Formation générale 2022 - Support AdHoc | 29685224 | 2022-08-02 | Champoux, Daniel | https://www.google.com/maps/place/Federal+Steel+Equipment+Ltd/@45.438671,-73.6842559,17z/data=!4m12!1m6!3m5!1s0x4cc916ed91b1a055:0x25f4359a9b7f9fcd!2sFederal+Steel+Equipment+Ltd!8m2!3d45.4386681!4d-73.6822375!3m4!1s0x4cc916ed91b1a055:0x25f4359a9b7f9fcd!8m2!3d45.4386681!4d-73.6822375 | 45.4387 | -73.6822 | 540 20e Avenue, Lachine, QC H8S 3T1 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=810
ServicesPLUS | SAP V10 Migration | Groupe Pro-Fab | 2022-11-30 | 2023-03-30 | New | 78 |  | 175 | CAD | 15697.5 | P20221212.0001 | Migration SAP B1 V9.1 vers V10 | 29685280 | 2022-12-06 | Champoux, Daniel | https://www.google.fr/maps/place/Groupe+Pro-Fab+-+Si%C3%A8ge+social/@46.6231521,-71.5027654,17z/data=!4m5!3m4!1s0x0:0x46eb83a9a3cadc17!8m2!3d46.6235537!4d-71.5004496!5m1!1e1?hl=fr | 46.6236 | -71.5004 | 294 Rue Laurier, Saint-Apollinaire, QC G0S 2E0 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=864
ServicesPLUS | Migration SAP B1 V10 SQL | Produit Electrolation | 2022-12-22 | 2023-03-30 | New | 46 |  | 165 | CAD | 8728.5 | P20221222.0001 | Migration V10 SQL | 29685283 | 2022-12-22 | Carriere, Daniel | https://www.google.fr/maps/place/Produits+Electrolation+Inc/@45.594032,-73.7443942,19z/data=!4m12!1m6!3m5!1s0x4cc92143ec29647d:0x9f89ab8988471bbd!2sProduits+Electrolation+Inc!8m2!3d45.5943373!4d-73.7441876!3m4!1s0x4cc92143ec29647d:0x9f89ab8988471bbd!8m2!3d45.5943373!4d-73.7441876!5m1!1e1?hl=fr | 45.5943 | -73.7442 | 990 Rue Bergar Laval QC H7L 5A1 CANADA | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=866
ServicesPLUS | Produmex WMS | Laiterie de Coaticook ltée | 2022-10-24 | 2023-03-31 | New | 166 | 1 | 165 | CAD | 31498.5 | P20221024.0001 | Produmex WMS | 29685255 | 2022-10-24 | Champoux, Daniel | https://www.google.fr/maps/place/Laiterie+de+Coaticook+Lt%C3%A9e/@45.1569719,-71.8032584,17z/data=!3m1!4b1!4m5!3m4!1s0x4cb658f0bcef7741:0xb18492fd3db72d09!8m2!3d45.1569295!4d-71.8010503!5m1!1e1?hl=fr | 45.1569 | -71.8011 | 1000 Rue Child, Coaticook, QC J1A 2S5 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=830&restoreworkspacekey=
En implantation | Implantation SAP B1 & Process Force | Fromagerie Polyethnique Inc | 2022-11-01 | 2023-12-31 | New | 815 | 1 | 170 | CAD | 159332.5 | P20221111.0001 | Projet implantation SAP B1 | 29685265 | 2022-11-11 | Dufour, Daniel | https://www.google.fr/maps/place/Fromagerie+Polyethnique+Inc./@45.9439944,-73.0552781,12.05z/data=!4m5!3m4!1s0x0:0xef280bcfed15fb50!8m2!3d45.9290294!4d-73.0172073!5m1!1e1?hl=fr | 45.929 | -73.0172 | 235 Chemin de St Robert, Saint-Robert, QC J0G 1S0 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=852
En implantation | Projet implantation SAP et WMS | Groupe Carreaux Céragrès Inc. | 2022-10-12 | 2023-12-29 | In Progress | 981 | 93.5 | 165 | CAD | 186144.75 | P20221012.0001 | Projet implantation SAP et WMS | 29685241 | 2022-10-12 | Dufour, Daniel | https://www.google.fr/maps/place/825+Rue+Deslauriers,+Saint-Laurent,+QC+H4N+1X3/@45.5292868,-73.667034,17z/data=!4m12!1m6!3m5!1s0x4cc9185f4cc42355:0xad548e4af066f4c6!2sGroupe+Carreaux+C%C3%A9ragr%C3%A8s+Inc.+(si%C3%A8ge+social)+-+Ceragres+Tile+Group+Inc.+(head+office)!8m2!3d45.5292868!4d-73.6648453!3m4!1s0x4cc9185f5a99d0af:0xb101086266c8cfcb!8m2!3d45.5292868!4d-73.6648453!5m1!1e1?hl=fr | 45.5293 | -73.6648 | 825 Deslaurier, Montreal QC H4N 1X3 | https://ww14.autotask.net/Mvc/Projects/ProjectDetail.mvc/ProjectDetail?gridConfiguration=Outline&initialContentPage=Summary&projectId=837
ServicesPLUS | Dubois Agrinovations - Archivage | Dubois Agrinovation Inc. | 2022-11-16 | 2023-05-06 | New | 33 | 3.5 | 170 | CAD | 6451.5 | P20221121.0001 | 2022 - Standard - Dubois Agrinovation (PLUS) | 29685117 | 2022-11-21 | Dufour, Daniel | https://www.google.fr/maps/place/Dubois+Agrinovation+-+%C3%89quipement+%26+Outils+d'Irrigation+et+Agricole/@45.2710103,-73.6095246,17z/data=!4m13!1m7!3m6!1s0x4cc97240123b9b5d:0x405a2402c5924169!2s478+Rue+Notre+Dame,+Saint-R%C3%A9mi,+QC+J0L+2L0!3b1!8m2!3d45.2710103!4d-73.6073359!3m4!1s0x4cc97240004f7b63:0xa00d36f88582c8ce!8m2!3d45.2708914!4d-73.607322!5m1!1e1?hl=fr | 45.271 | -73.6073 | 478 Rue Notre Dame, Saint-Rémi, QC J0L 2L0 | https://ww14.autotask.net/Mvc/Framework/Navigation.mvc/Landing?restoreworkspacekey=z3f7cb84a3a934ef3ad2d0dc3eee18d6c
|  | Forgestik - Quebec | [7 empty] | 0 | [5 empty] | https://www.google.fr/maps/place/Forgestik+Inc.+-+Qu%C3%A9bec/@46.7678083,-71.2910004,17z/data=!4m5!3m4!1s0x0:0x3410c520d6b20abc!8m2!3d46.7677269!4d-71.2887151!5m1!1e1?hl=fr | 46.7677 | -71.2887 | 2828 Bd Laurier #700, Québec, QC G1V 0B9
|  | Forgestik-Montreal | [7 empty] | 0 | [5 empty] | https://www.google.fr/maps/place/Forgestik+Inc+-+Montreal+Head+Office/@45.5219334,-73.6152552,17z/data=!3m1!4b1!4m5!3m4!1s0x4cc9199df6b7f653:0x801060272b57c4f4!8m2!3d45.52193!4d-73.6130697!5m1!1e1?hl=fr | 45.5219 | -73.6131 | 797 Champagneur Avenue, Outremont, Quebec, H2V 3P9
|  | Forgestik - Vancouver | [7 empty] | 0 | [5 empty] | https://www.google.fr/maps/place/Forgestik+Inc+-+Vancouver/@49.2838546,-123.121829,17z/data=!3m1!5s0x548671a3d041e691:0x16e05f12b932f59a!4m12!1m6!3m5!1s0x54867181e140b2c3:0x3257d5499dc7de7c!2sForgestik+Inc+-+Vancouver!8m2!3d49.2838546!4d-123.1196403!3m4!1s0x54867181e140b2c3:0x3257d5499dc7de7c!8m2!3d49.2838546!4d-123.1196403!5m1!1e1?hl=fr | 49.2839 | -123.1196 | 885 W Georgia St #1500, Vancouver, BC V6C 3E8
|  | Forgestik - Toronto | [7 empty] | 0 | [5 empty] | https://www.google.fr/maps/place/Forgestik+Inc.+-+Toronto/@43.6410825,-79.3809083,17z/data=!3m1!5s0x882b3757de085e91:0xc359f58994eb5f5!4m12!1m6!3m5!1s0x89d4cb2ae8a1ac2d:0xe007d130adfb1a56!2sForgestik+Inc.+-+Toronto!8m2!3d43.6410825!4d-79.3787196!3m4!1s0x89d4cb2ae8a1ac2d:0xe007d130adfb1a56!8m2!3d43.6410825!4d-79.3787196!5m1!1e1?hl=fr | 43.6411 | -79.3787 | 88 Queens Quay W #2500, Toronto, ON M5J 0B9